## WAN
SN | Ticket No | W/O | Date | Team | Alert Type | Issue Type | Initial Findings | Node ID | Cabinet Asset Field Tag | Location | Coordinates | Area Category | Severity | Fault Notification Date and Time (dd/mm/yy hh:mm) | Fault Response Date and Time (dd/mm/yy hh:mm) | FRT Fault Response Time (Minutes) | Actual Start Date and Time (dd/mm/yy hh:mm) | Actual Finish Date and Time (dd/mm/yy hh:mm) | ART Active Repair Time (Minutes) | TRT Total Repair Time (Minutes) | Action Taken | Status | Fault Attribution | FA Class | FA Notes | Remarks
1 | NA | NA | 2026-02-01 | - | Node Down | Network down | FLM visited the site and confirmed that Kahramaa power was not available at the cabinet. | P010-ENC61-CE-01 |  | Zone 57 | 51.4699752, 25.170097 | Outside Doha | Critical | 2026-02-01 08:39 | 2026-02-01 08:39 | 0 | 2026-02-01 08:39 | 2026-02-01 13:57 | 318 | 318 | Power was restored by Kahramaa after 5 hours and 17 minutes.Network was up. | Completed | Non-maintainer | 3rd Party | State Kahramaa | Network Back Online
2 | NA | NA | 2026-02-02 | - | Node Down | Network down | Link went down | SAL-ENC45-CE-01 |  | Zone 83 | 51.042739, 25.005944 | Outside Doha | Critical | 2026-02-02 13:04 | 2026-02-02 13:04 | 0 | 2026-02-02 13:04 | 2026-02-02 13:08 | 4 | 4 | Link restored after 4 mins(Auto) # It is pending from TTG | Completed | Non-maintainer | 3rd Party | TTG | Network Back Online
3 | NA | NA | 2026-02-02 | - | Node Down | Network down | network went down due to system upgrade | P008C2-Enc09-CE01 |  | - | - | - | Critical | 2026-02-02 06:49 | 2026-02-02 06:49 | 0 | 2026-02-02 06:49 | 2026-02-02 06:50 | 1 | 1 | Escalated to Salam Tech team (Imran) on phone and rebooted the system | Completed | Non-maintainer | 3rd Party | Salam Tech | Network Back Online
4 | NA | NA | 2026-02-04 | Vishnu | Node Down | Device Down | Power failure detected at the site | Sal-ENC38-CE-01 |  | Zone 83 | 51.1144427, 25.069908 | Outside Doha | Critical | 2026-02-04 07:00 | 2026-02-04 07:00 | 0 | 2026-02-04 08:00 | 2026-02-04 13:52 | 352 | 412 | The Kahramaa team is currently performing maintenance on the main electrical poles in the area.Expected Completion: Restoration is anticipated by 2:00 PM. | Completed | Non-maintainer | 3rd Party | State Kahramaa | Network Back Online
5 | NA | NA | 2026-02-05 | - | Node Down | Link Down | Link went down | SAL-ENC45-CE-01 |  | Zone 83 | 51.042739, 25.005944 | Outside Doha | Critical | 2026-02-05 12:47 | 2026-02-05 12:47 | 0 | 2026-02-05 12:47 | 2026-02-05 12:50 | 3 | 3 | Link restored after 3 mins(Auto) # It is pending from TTG | Completed | Non-maintainer | 3rd Party | TTG | Network Back Online
6 | NA | NA | 2026-02-05 | - | Node Down | Link Down | Link went down | SAL-ENC45-CE-01 |  | Zone 83 | 51.042739, 25.005944 | Outside Doha | Critical | 2026-02-05 14:25 | 2026-02-05 14:25 | 0 | 2026-02-05 14:25 | 2026-02-05 14:36 | 11 | 11 | Link restored after 11 mins(Auto) # It is pending from TTG | Completed | Non-maintainer | 3rd Party | TTG | Network Back Online
7 | NA | NA | 2026-02-06 | Vishnu | Node Down | Device Down | UPS was not giving output | P010-ENC61–CE-01 |  | Zone 57 | 51.4699752, 25.170097 | Outside Doha | Critical | 2026-02-06 09:36 | 2026-02-06 09:36 | 0 | 2026-02-06 11:01 | 2026-02-06 11:08 | 7 | 92 | Issue resolved after restarting UPS | Completed | Maintainer | N/a | N/a | Network Back Online
8 | NA | NA | 2026-02-07 | Vishnu | Node Down | Device Down | Noticed no power on Main breakers/Terminals | P023C1-ENC01–CE -01 |  | Zone 91 | 51.583897, 25.111748 | Outside Doha | Critical | 2026-02-07 11:25 | 2026-02-07 11:25 | 0 | 2026-02-07 12:02 | 2026-02-07 13:13 | 71 | 108 | Power supply restored by Kahrama staff.KAHRAMAA reference No. 261100005225 | Completed | Non-maintainer | 3rd Party | State Kahramaa | Network Back Online
9 | NA | NA | 2026-02-07 | Vishnu | Node Down | Device Down | Noticed no power on Main breakers/Terminals | P023C1-ENC01–UPE -01 |  | Zone 91 | 51.583897, 25.111748 | Outside Doha | Critical | 2026-02-07 11:25 | 2026-02-07 11:25 | 0 | 2026-02-07 12:02 | 2026-02-07 13:13 | 71 | 108 | Power supply restored by Kahrama staff.KAHRAMAA reference No. 261100005225 | Completed | Non-maintainer | 3rd Party | State Kahramaa | Network Back Online
10 | NA | NA | 2026-02-08 | Salem/Amr | Node Down | Device Down | MCB was tripped at site | SAL-ENC50–CE -01 |  | Zone 96 | 50.9993542, 24.9513076 | Outside Doha | Critical | 2026-02-08 12:29 | 2026-02-08 12:29 | 0 | 2026-02-08 13:34 | 2026-02-08 14:00 | 26 | 91 | team turned on the CB and device restored | Completed | Maintainer | N/a | N/a | Network Back Online
11 | NA | NA | 2026-02-09 | Salem/Amr | Node Down | Device Down | Link went down | P008C3-ENC01–CE -01 |  | Zone 55 | 51.4801647, 25.2614822 | Outside Doha | Critical | 2026-02-09 15:06 | 2026-02-09 15:06 | 0 | 2026-02-09 15:06 | 2026-02-09 15:08 | 2 | 2 | Escalated to Salam Tech team (Imran) on phone and rebooted the system | Completed | Non-maintainer | 3rd Party | Salam Tech | Network Back Online
12 | NA | NA | 2026-02-09 | Salem/Amr | Node Down | Device Down | Link went down | P008C3-ENC25–CE -01 |  | Zone 56 | 51.50261, 25.2341068 | Outside Doha | Critical | 2026-02-09 15:43 | 2026-02-09 15:43 | 0 | 2026-02-09 15:43 | 2026-02-09 15:45 | 2 | 2 | Escalated to Salam Tech team (Imran) on phone and rebooted the system | Completed | Non-maintainer | 3rd Party | Salam Tech | Network Back Online
13 | NA | NA | 2026-02-10 | Salem/Amr | Node Down | Link Down | MCB was tripped at site | P005-ENC410-CE-01 |  | Zone 56 | 51.399465, 25.3102445 | Outside Doha | Critical | 2026-02-10 13:39 | 2026-02-10 13:39 | 0 | 2026-02-10 14:14 | 2026-02-10 15:52 | 98 | 133 | Team turned on the CB and device restored | Completed | Maintainer | N/a | N/a | Network Back Online
14 | NA | NA | 2026-02-10 | Salem/Amr | Node Down | Link Down | Link went down | SAL-ENC45-CE-01 |  | Zone 83 | 51.042739, 25.005944 | Outside Doha | Critical | 2026-02-10 16:19 | 2026-02-10 16:19 | 0 | 2026-02-10 16:19 | 2026-02-10 16:26 | 7 | 7 | Link went down and restored after 7 mins(Auto) # It is pending from TTG | Completed | Non-maintainer | 3rd Party | TTG | Network Back Online
15 | NA | NA | 2026-02-11 | Salem/Amr | Node Down | Link Down | Link went down | SAL-ENC45-CE-01 |  | Zone 83 | 51.042739, 25.005944 | Outside Doha | Critical | 2026-02-11 12:59 | 2026-02-11 12:59 | 0 | 2026-02-11 12:59 | 2026-02-11 13:09 | 10 | 10 | Link went down and restored after 10 mins(Auto) # It is pending from TTG | Completed | Non-maintainer | 3rd Party | TTG | Network Back Online
16 | NA | NA | 2026-02-11 | Salem/Amr | Node Down | Link Down | Link went down | SAL-ENC45-CE-01 |  | Zone 83 | 51.042739, 25.005944 | Outside Doha | Critical | 2026-02-11 13:10 | 2026-02-11 13:10 | 0 | 2026-02-11 13:10 | 2026-02-11 13:18 | 8 | 8 | Link went down and restored after 8 mins(Auto) # It is pending from TTG | Completed | Non-maintainer | 3rd Party | TTG | Network Back Online
17 | NA | NA | 2026-02-11 | Salem/Amr | Node Down | Link Down | Link went down | SAL-ENC45-CE-01 |  | Zone 83 | 51.042739, 25.005944 | Outside Doha | Critical | 2026-02-11 16:09 | 2026-02-11 16:09 | 0 | 2026-02-11 16:09 | 2026-02-11 16:15 | 6 | 6 | Link went down and restored after 6 mins(Auto) # It is pending from TTG | Completed | Non-maintainer | 3rd Party | TTG | Network Back Online
18 | NA | NA | 2026-02-11 | Vishnu/Amr | Node Down | Link Down | RJ45 cable was loose from switch to CCTV POE | SAL-ENC45-CE-01 |  | Zone 83 | 51.042739, 25.005944 | Outside Doha | Critical | 2026-02-11 18:31 | 2026-02-11 18:34 | 3 | 2026-02-11 19:21 | 2026-02-11 20:14 | 53 | 103 | RJ45 cable cleaned and fixed properly | Completed | Maintainer | N/a | N/a | Network Back Online
19 | NA | NA | 2026-02-12 | Vishnu/Amr | Node Down | Device Down | NA | SAL-ENC26-CE-01 |  | zone 56 | 51.2478413 25.1435454 | Outside Doha | Critical | 2026-02-12 17:16 | 2026-02-12 17:18 | 2 | 2026-02-12 17:18 | 2026-02-12 17:39 | 21 | 23 | Device Restored(Auto) | Completed | Maintainer | N/a | N/a | Network Back Online
20 | NA | NA | 2026-02-14 | Vishnu/Amr | Node Down | Device Down | NA | SAL-ENC20-CE-01,SAL-ENC14-CE-01,SAL-ENC20-UPE-02 |  | zone 56 | 51.3063942 25.164986 | Outside Doha | Critical | 2026-02-14 16:22 | 2026-02-14 16:25 | 3 | 2026-02-14 16:25 | 2026-02-14 16:54 | 29 | 32 | Device Restored(Auto) | Completed | Maintainer | N/a | N/a | Network Back Online
21 | Sirti-WAN-R3-Ticket-01 | NA | 2026-02-15 | Vishnu/Amr | Node Down | Device Down | FLM visited the site and found no kahramaa power in cabinet as well as FP | P028C2-ENC18-CE-01,P028C2-ENC25-CE-01,P028C2-ENC25-UPE-01 |  | Zone 18 | 25.28983, 51.51513 | Inside Doha | Critical | 2026-02-15 07:13 | 2026-02-15 07:15 | 2 | 2026-02-15 07:20 | 2026-02-15 08:48 | 88 | 95 | FLM Team contacted kharamaa and they restored the power | Completed | Non-maintainer | 3rd Party | State Kahramaa | Network Back Online
22 | Sirti-WAN-R3-Ticket-02 | NA | 2026-02-15 | Vishnu/Amr | Node Down | Device Down | FLM visited the site and found no kahramaa power in cabinet as well as FP | SAL-ENC45-CE-01 |  | Zone 83 | 51.042739, 25.005944 | Outside Doha | Critical | 2026-02-15 07:44 | 2026-02-15 07:46 | 2 | 2026-02-15 08:31 | 2026-02-15 12:06 | 215 | 262 | Power restored by kharamaa team raised a ticket.Ref No-261100006258 | Completed | Non-maintainer | 3rd Party | State Kahramaa | Network Back Online
23 | Sirti-WAN-R3-Ticket-03 | NA | 2026-02-15 | Saleem/Amr | Node Down | Link Down | FLM visited the site and found port 05 down which is connected to LAN access switch | 22FEB-ENC25-CE-01 |  | Zone 34 | 51.47088144, 25.31832397 | Inside Doha | Critical | 2026-02-15 11:38 | 2026-02-15 11:47 | 9 | 2026-02-15 11:47 | 2026-02-15 13:08 | 81 | 90 | The Alarm was cleared after LAN device came up | Completed | Maintainer | N/a | N/a | Network Back Online
24 | Sirti-WAN-R3-Ticket-04 | NA | 2026-02-16 | Amr | Node Down | Device Down | NA | P010-ENC61-CE-01,P010-ENC64-CE-01 |  | - | 51.4699752 25.1700975 | - | Critical | 2026-02-16 09:23 | 2026-02-16 09:24 | 1 | 2026-02-16 09:24 | 2026-02-16 09:40 | 16 | 17 | Device Restored(Auto) | Completed | Maintainer | N/a | N/a | Network Back Online
25 | Sirti-WAN-R3-Ticket-05 | NA | 2026-02-17 | Vishnu/Haroon | No Power Redeundancy | Power Module Power off | MCB was tripped at SMDB | P012-ENC97-UPE-02 |  | Zone 56 | 25.1926322 51.4542203 | Outside Doha | Critical | 2026-02-17 16:37 | 2026-02-17 16:41 | 4 | 2026-02-17 17:02 | 2026-02-17 22:36 | 334 | 359 | FLM Turned on the CB and device restored | Completed | Non-maintainer | Access | Got the key from the Tunnel contractor and turned on the CB | Network Back Online
26 | Sirti-WAN-R3-Ticket-06 | NA | 2026-02-20 | Aneesh/Abubaker | Node Down | Device Down | P023C2-ENC16-CE-01 & P023C2-ENC16-UPE-02 unreachable from eSite | P023C2-ENC16-CE-01 & P023C2-ENC16-UPE-02 |  | Zone 82 | 25.228079 51.307359 | Outside Doha | Critical | 2026-02-20 04:33 | 2026-02-20 04:42 | 9 | 2026-02-20 06:50 | 2026-02-20 07:10 | 20 | 157 | FLM Turned on the CB and devices restored | Completed | Maintainer | N/a | N/a | Network Back Online
27 | Sirti-WAN-R3-Ticket-07 | NA | 2026-02-20 | Mastan/Adil | Node Down | Device Down | Port Down at CE Connected to Lan 2 Switch | SAL-ENC20-CE-01 |  | - | - | - | Critical | 2026-02-20 08:48 | 2026-02-20 09:00 | 12 | 2026-02-20 09:00 | 2026-02-20 09:04 | 4 | 16 | Device Restored(Auto) | Completed | Maintainer | N/a | N/a | Network Back Online
28 | Sirti-WAN-R3-Ticket-08 | NA | 2026-02-21 | Haroon/Masthan | Ethernet link down | Link Down | Eth link down RMC-P003 &SOC-P003 &P004-SOC PRI due QNBN activity on the link | RMC-P003 &SOC-P003 &P004-SOC PRI | - | - | - | - | Critical | 2026-02-21 12:21 | 2026-02-21 12:24 | 3 | 2026-02-21 12:24 | 2026-02-21 16:26 | 242 | 245 | Activity was finished and link was restored | Completed | Non-maintainer | 3rd Party | QNBN activity on the link | Network Back Online
29 | Sirti-WAN-R3-Ticket-09 | NA | 2026-02-22 | AMR / Vishnu | Device Down | Device Down | NA | P028C2-ENC04-CE-01-OMC LOCAL | - | - | - | - | Critical | 2026-02-22 10:32 | 2026-02-22 10:35 | 2.8333 | 2026-02-22 10:35 | 2026-02-22 10:44 | 9 | 11.8333 | Alarm Auto Cleared before flm visit the site | Completed | Maintainer | N/a | N/a | Network Back Online
30 | Sirti-WAN-R3-Ticket-10 | NA | 2026-02-22 | AMR / Erick | Link Down | Link Down | TTG team was working at RMC Datacenter on RMC-ENC-NMS-SW-01 SERVER as a part of snag clearanace | RMC-ENC-NMS-SW-01 SERVER | - | - | - | - | Critical | 2026-02-22 11:52 | 2026-02-22 11:53 | 1 | 2026-02-22 11:52 | 2026-02-22 12:03 | 11.25 | 11.25 | Alarm Auto Cleared | Completed | Non-maintainer | 3rd Party | TTG team was working at RMC Datacenter | Network Back Online
31 | Sirti-WAN-R3-Ticket-11 | NA | 2026-02-22 | AMR / Haroon / Erick | Port Module Offline | One Power Source is Down | Power cable loose between DWDM and PDU | RAA_SEC | - | Zone 28 | 25.285228, 51.551657 | Inside Doha | Critical | 2026-02-22 10:54 | 2026-02-22 10:54 | 0 | 2026-02-22 10:54 | 2026-02-22 15:24 | 269 | 269 | FLM Visit the site and found the low voltage and fix the power source | Completed | Maintainer | N/a | N/a | Network Back Online
32 | Sirti-WAN-R3-Ticket-12 | NA | 2026-02-23 | HAROON | High Temprature | LPU Board 2 | Boards Temprature higher than the upper threshold | P060-ENC18-UPE-01 | - | - | - | - | Critical | 2026-02-23 14:28 | 2026-02-23 14:30 | 2 | 2026-02-23 14:30 | 2026-02-23 14:38 | 8 | 10 | Alarm Auto Cleared before flm visit the site | Completed | Maintainer | N/a | N/a | Network Back Online
33 | Sirti-WAN-R3-Ticket-13 | NA | 2026-02-24 | Adel / Umair | Device Down | Device Down | Breaker off from the FP side | P023C3-ENC174-UPE02 & P023C3-ENC174-CE 01 | - | Zone 94 | 25.01688 51.49047 | Outside Doha | Critical | 2026-02-24 03:48 | 2026-02-24 03:52 | 5 | 2026-02-24 05:01 | 2026-02-24 05:20 | 19.5 | 92.5 | MCB was tripped , FLM switched on the MCB | Completed | Maintainer | N/a | N/a | Network Back Online
34 | Sirti-WAN-R3-Ticket-14 | NA | 2026-02-24 | AMR | Communication betweeen NMS and NE is Abnormal | Device Down | NA | DUK-ENC04-CE-01 | - | - | - | - | Critical | 2026-02-24 10:23 | 2026-02-24 10:29 | 6 | 2026-02-24 10:29 | 2026-02-24 10:46 | 16.2833 | 22.2833 | Alarm Auto Cleared | Completed | Maintainer | N/a | N/a | Network Back Online
35 | Sirti-WAN-R3-Ticket-15 | NA | 2026-02-24 | AMR | Link Down | Link Down | NA | DUK-ENC06-CE-01 | - | - | - | - | Critical | 2026-02-24 11:47 | 2026-02-24 11:47 | 0 | 2026-02-24 11:47 | 2026-02-24 12:12 | 24.7333 | 24.7333 | Alarm Auto Cleared | Completed | Maintainer | N/a | N/a | Network Back Online
36 | Sirti-WAN-R3-Ticket-16 | NA | 2026-02-24 | HAROON\Masthan | High Temprature | LPU Board 2 Heatup | Boards Temprature higher than the upper threshold | P060-ENC18-UPE-01 | - | Zone 70 | 25.388045, 51.488990 | Outside Doha | Critical | 2026-02-24 13:09 | 2026-02-24 13:10 | 1 | 2026-02-24 13:30 | 2026-02-24 15:21 | 111 | 132 | FLM Visit the site and Turn on the AC Breaker and restore the Cooling | Completed | Maintainer | N/a | N/a | Network Back Online
37 | Sirti-WAN-R3-Ticket-17 | NA | 2026-02-25 | AMR / Vishnu | Communication betweeen NMS and NE is Abnormal | Device Down / Link Down | There was no power supply in main terminals of DGME-23 | P059-C1-ENC23-CE-01 P059-C1-ENC23-UPE-02 P059-C1-ENC04-UPE-01 P059-C1-ENC42-CE-01 | - | Zone 71 | 25.451633, 51.409080 | Outside Doha | Critical | 2026-02-25 08:13 | 2026-02-25 08:14 | 1 | 2026-02-25 08:57 | 2026-02-25 10:20 | 83.25 | 127.25 | Switched the Circuit from Primary to Secondary in ATS at Feeder side(ITS FP-16) | Completed | Maintainer | N/a | N/a | Network Back Online
38 | Sirti-WAN-R3-Ticket-18 | NA | 2026-02-26 | AMR / Vishnu | Link Down | Link Down | Other Ashghal Contractor (ITS Qatar) was doing the maintenance for PTZ Camera)-On NMS port down GE1/0/15 -Huawei Switch | DUK-ENC12-CE-01 | - | Zone 80 | 25.430216, 51.149749 | Outside Doha | Critical | 2026-02-26 08:04 | 2026-02-26 08:06 | 2 | 2026-02-26 08:04 | 2026-02-26 08:42 | 37.7667 | 37.7667 | FME arrived at the site and found that ITS Qatar was performing maintenance on the PTZ camera. After the maintenance was completed, the alarm was cleared-Verified the ports in Huawei Switch, all were working well | Completed | Non-maintainer | 3rd Party | ITS Qatar was performing maintenance | Network Back Online
39 | Sirti-WAN-R3-Ticket-19 | NA | 2026-02-26 | AMR / Vishnu | Link Down | Link Down | NA -On NMS port down GE1/0/15 -Huawei Switch | SAL-ENC45-CE-01 | - | Zone 83 | 51.042739, 25.005944 | Outside Doha | Critical | 2026-02-26 08:24 | 2026-02-26 08:26 | 2 | 2026-02-26 08:26 | 2026-02-26 08:47 | 21 | 23 | FME arrived Verified the ports in Huawei Switch, all were working well- Link went down and restored after 22 min 49 sec | Completed | Maintainer | N/a | N/a | Network Back Online
40 | Sirti-WAN-R3-Ticket-20 | NA | 2026-02-26 | AMR / Vishnu | Link Down | Link Down | NA -On NMS port down GE1/0/9 -Huawei Switch | DUK-ENC16-CE-01 | - | Zone 80 | 25.432295, 51.110656 | Outside Doha | Critical | 2026-02-26 09:02 | 2026-02-26 09:04 | 2 | 2026-02-26 09:11 | 2026-02-26 09:25 | 14 | 23 | FME arrived Verified the ports in Huawei Switch, all were working well- Link went down and restored after 22 min 12 sec | Completed | Maintainer | N/a | N/a | Network Back Online
41 | Sirti-WAN-R3-Ticket-21 | NA | 2026-02-26 | AMR / Vishnu | Link Down | Link Down | NA -On NMS port down GE1/0/10 -Huawei Switch | SAL-ENC50-CE-01 | - | Zone 96 | 24.951308, 50.999354 | Outside Doha | Critical | 2026-02-26 10:21 | 2026-02-26 10:21 | 0 | 2026-02-26 10:29 | 2026-02-26 10:45 | 16 | 24 | FME arrived Verified the ports in Huawei Switch, all were working well- Link went down and restored after 22 min 12 sec | Completed | Maintainer | N/a | N/a | Network Back Online
42 | Sirti-WAN-R3-Ticket-22 | NA | 2026-02-26 | AMR / Vishnu | Communication betweeen NMS and NE is Abnormal | Communication betweeen NMS and NE is Abnormal | Issue Esclated to Imran (SALAM TECH) by call and whats app messages | P008-C3-ENC19-CE-01 P008-C3-ENC09-CE-01 P008-C3-ENC05-CE-01 P008-C3-ENC07-CE-01 P008-C3-ENC04-CE-01 P008-C3-ENC01-CE-01 | - | - | - | - | Critical | 2026-02-26 10:31 | 2026-02-26 10:31 | 0 | 2026-02-26 10:31 | 2026-02-26 11:35 | 64.1833 | 64.1833 | Issue Esclated to Imran (SALAM TECH) by call and whats app messages - All alarms got cleared | Completed | Non-maintainer | 3rd Party | Salam Tech | Network Back Online
43 | Sirti-WAN-R3-Ticket-23 | NA | 2026-02-27 | HAROON / Patric | Heat Alarm | SFP Interface Heat Alarm | Optical Module temp too high | P010-ENC01-CE-01 | - | Zone 81 | 25.139881, 51.407393 | Outside Doha | Critical | 2026-02-27 12:08 | 2026-02-27 12:11 | 3 | 2026-02-27 12:11 | 2026-02-27 15:35 | 204 | 207 | Alarm is about SFP interface heatup overall device stats are normal, no Service Effected.alarms got cleared | Completed | Maintainer | N/a | N/a | Network Back Online
44 | Sirti-WAN-R3-Ticket-24 | NA | 2026-02-28 | AMR | Link Down | Link Down | NA | SAL-ENC67-CE-01 | - | - | - | - | Critical | 2026-02-28 11:06 | 2026-02-28 11:06 | 0 | 2026-02-28 11:06 | 2026-02-28 11:23 | 17.05 | 17.05 | Link went down and restored Auto | Completed | Maintainer | N/a | N/a | Network Back Online
45 | Sirti-WAN-R3-Ticket-25 | NA | 2026-03-03 | AMR | Link Down | Link Down | NA | DUK-ENC34-CE-01 | - | Zone 72 | 25.4537767 50.8835078 | Outside Doha | Critical | 2026-03-03 12:18 | 2026-03-03 12:18 | 0 | 2026-03-03 12:18 | 2026-03-03 12:45 | 27.05 | 27.05 | Issue esclated to RMC team and they have update Team is doing PM for End device | Completed | Non-maintainer | 3rd Party | RMC | Network Back Online
46 | Sirti-WAN-R3-Ticket-26 | NA | 2026-03-04 | AMR | PWR Module Stopped Working | Power Module Power off | PDU Was OFF | RAA-TCR-USG-02 / DWDM RAA_SEC | - | Zone 18 | 25.28522778 51.55165688 | Inside Doha | Critical | 2026-03-04 08:22 | 2026-03-04 08:24 | 2 | 2026-03-04 09:00 | 2026-03-04 09:36 | 36.7667 | 74.7667 | FLM Turned on the CB and device restored | Completed | Maintainer | N/a | N/a | Network Back Online
47 | Sirti-WAN-R3-Ticket-27 | NA | 2026-03-04 | AMR | ASH_WDM_RAA-P015-OSC_Protection ASH_WDM_RAA-P012-OSC_Protection ASH_WDM_SOC-P012-OCH-CH-54_Protection_L ASH_WDM_RMC-P012-OCH-CH-56_Protection_L ASH_WDM_SOC-P015-OCH-CH-58_Protection_S ASH_WDM_RMC-P015-OCH-CH-60_Protection_L | RAA_Sec Subrack 2 was down due to power issue | PWR cable at PDU side was loose | DWDM RAA_SEC | - | Zone 18 | 25.28522778 51.55165688 | Inside Doha | Critical | 2026-03-04 09:20 | 2026-03-04 09:20 | 0 | 2026-03-04 09:20 | 2026-03-04 09:52 | 32.7833 | 32.7833 | FLM fixed the loose power cable connection by cable tie /to be plan for PDU replacement | Completed | Maintainer | N/a | N/a | Network Back Online
48 | Sirti-WAN-R3-Ticket-28 | NA | 2026-03-08 | Abubakr | Power Module Powered off | Power Module Power off | khahromaa power shutdown | - P004-TMC-NPE-01 - P004_Pri - P004_Sec | - |  | 25.319385,51.352255 | Outside Doha | Critical | 2026-03-08 05:23 | 2026-03-08 05:28 | 5.4833 | 2026-03-08 05:23 | 2026-03-08 07:01 | 98.8333 | 98.8333 | Main Power was down due to power outage from KAHRAMAA side, Alarms cleared after KAHRAMAA power recovered by KAHRAMAA team | Completed | Non-maintainer | 3rd Party | State Kahramaa | Network Back Online
49 | Sirti-WAN-R3-Ticket-29 | NA | 2026-03-08 | AMR | Communication betweeen NMS and NE is Abnormal | Device Down | Team found no PWR at ENC / FP CB was tripped | P004-ENC43-UPE-02 P004-ENC43-CE-01 P023C2-ENC43-CE-01 | - |  |  |  | Critical | 2026-03-08 17:23 | 2026-03-08 17:27 | 4 | 2026-03-08 17:23 | 2026-03-08 18:19 | 55.5 | 55.5 | The FME team reached the site and found that there was no power in the ENC cabinet. Upon checking the FP cabinet, they found that the main circuit breaker (CB) was in the OFF (tripped) state. The CB was switched ON, after which all devices were restored and the alarms were cleared | Completed | Maintainer | N/a | N/a | Network Back Online
50 | Sirti-WAN-R3-Ticket-30 | NA | 2026-03-09 | Adel | Communication betweeen NMS and NE is Abnormal | Device Down | Team found no output power from UPS | P010-ENC61-CE-01 | - |  | 25.1700975° ,51.4699752° | Outside Doha | Critical | 2026-03-09 08:00 | 2026-03-09 08:06 | 6.25 | 2026-03-09 08:00 | 2026-03-09 09:45 | 105.5167 | 105.5167 | there was no UPS output power , FLM Turned on the UPS | Completed | Non-maintainer | 3rd Party | RMC | Network Back Online
51 | Sirti-WAN-R3-Ticket-31 | NA | 2026-03-09 | Adel | power module stopped working , power fail | power fail | alarm is auto clear before visiting the site | P004-TMC-NPE-01 P004-sec P004-pri |  |  | 25.319385 ,51.352255 | Outside Doha | Critical | 2026-03-09 10:14 | 2026-03-09 10:17 | 3.1833 | 2026-03-09 10:14 | 2026-03-09 10:29 | 15.5167 | 15.5167 | alarm is auto clear before visiting the site | Completed | Non-maintainer | N/a | N/a | Network Back Online
52 | Sirti-WAN-R3-Ticket-30 | NA | 2026-03-09 | Adel | Communication betweeen NMS and NE is Abnormal | Device Down | Team found no output power from UPS | P010-ENC61-CE-01 | - |  | 25.1700975° ,51.4699752° | Outside Doha | Critical | 2026-03-09 10:36 | 2026-03-09 10:40 | 4.2667 | 2026-03-09 10:36 | 2026-03-09 11:14 | 37.9667 | 37.9667 | there was no UPS output power , FLM Turned on the UPS | Completed | Non-maintainer | 3rd Party | RMC | Network Back Online
53 | Sirti-WAN-R3-Ticket-30 | NA | 2026-03-09 | Adel | Communication betweeen NMS and NE is Abnormal | Device Down | Team found no output power from UPS | P010-ENC61-CE-01 |  |  | 25.1700975° ,51.4699752° | Outside Doha | Critical | 2026-03-09 12:14 | 2026-03-09 12:18 | 4 | 2026-03-09 12:14 | 2026-03-09 13:26 | 71.9 | 71.9 | there was no UPS output power , FLM Turned on the UPS, disconnected the AC from the UPS | Completed | Non-maintainer | 3rd Party | RMC | Network Back Online
54 | Sirti-WAN-R3-Ticket-31 | NA | 2026-03-09 | AMR | Communication betweeen NMS and NE is Abnormal | Device Down | NA | P010-ENC61-CE-01 |  |  |  |  | Critical | 2026-03-09 15:38 | 2026-03-09 15:38 | 0 | 2026-03-09 15:38 | 2026-03-09 15:49 | 10.9167 | 10.9167 | Alarm is auto clear before visiting the site | Completed | Non-maintainer | 3rd Party | RMC | Network Back Online
55 | Sirti-WAN-R3-Ticket-32 | NA | 2026-03-10 | Adel | Communication betweeen NMS and NE is Abnormal | Device Down | tripped CB | P029C2-ENC05-CE-01 |  |  | 25.281278° ,51.503972° | inside Doha | Critical | 2026-03-10 07:33 | 2026-03-10 07:36 | 3 | 2026-03-10 07:33 | 2026-03-10 09:13 | 100 | 100 | FLM switched on tripped CB | Completed | Maintainer | N/a | N/a | Network Back Online
56 | Sirti-WAN-R3-Ticket-33 | NA | 2026-03-10 | Adel | Communication betweeen NMS and NE is Abnormal | Device Down | alarm is auto clear before visiting the site | SAL-ENC63-CE-01 |  |  | 24.8301249° ,50.8705931° | Outside Doha | Critical | 2026-03-10 12:15 | 2026-03-10 12:18 | 4 | 2026-03-10 12:15 | 2026-03-10 13:12 | 58 | 58 | Alarm is auto clear before visiting the site | Completed | Non-maintainer | N/a | N/a | Network Back Online
57 |  | NA
58 |  | NA
59 |  | NA
60 |  | NA
61 |  | NA
62 |  | NA
63 |  | NA
64 |  | NA
65 |  | NA
66 |  | NA
67 |  | NA
68 |  | NA
69 |  | NA
70 |  | NA
71 |  | NA
72 |  | NA
73 |  | NA

## Legend
Maintainer | N/a | N/a |  |  | Maintainer | N/a | N/a
Non-maintainer | Access | no keys, police not allow |  |  | Non-maintainer | Access | no keys, police not allow
| Environmental | flooding, dust storm |  |  |  | Environmental | flooding, dust storm
| 3rd party | car crash, Bin omran contractor damage |  |  |  | 3rd party | car crash, Bin omran contractor damage
|  |  | Inside Doha | Critical | fault showed on system | team dispatched |  | reach site | finish repair
|  |  | Outside Doha | High
Medium
Low